AI HOME STYLING PLATFORM

MVP Development & Launch Roadmap

Saudi Arabia Market

A Joint Venture by KASA Design & GulfBoost

Danah (CEO, KASA Design)  |  Yousef (GulfBoost, Technical Lead)

February 2026  |  Confidential

# 1. Executive Summary

This roadmap translates the AI Home Styling Platform MVP vision into a concrete, phased plan for KASA Design and GulfBoost to co-develop, launch, and position for fundraising in the Saudi Arabian market. The platform sits at the intersection of AI image generation and furniture e-commerce, targeting a KSA online furniture market projected to reach SAR 49 billion (~$13B) by 2034, growing at 19% CAGR.

The core proposition: users upload a room photo, set style and budget preferences, receive photorealistic AI-styled concepts, and buy every item they see in a single checkout. No designers, no consultations — just confidence, clarity, and commerce.

All pricing, payment infrastructure, legal compliance, and supplier partnerships in this document are specifically tailored for the Kingdom of Saudi Arabia, with all user-facing currency in Saudi Riyals (SAR).

# 2. Honest Assessment of the MVP Document

## 2.1 What the MVP Gets Right

The positioning is strong. Framing the platform as a "confidence engine tied directly to commerce" rather than a design tool is a genuine differentiator. The user flow (upload, set preferences, AI styles, swap/refine, lock and buy) is intuitive and commercially sound. The commission-based revenue model (10–20% on furniture sales) is proven in adjacent markets and aligns incentives with user success.

The competitive analysis correctly identifies that existing tools (RoomGPT, Interior AI, Collov) generate images but do not close the commerce loop. That gap is real and valuable.

## 2.2 What Needs Tightening

### Scope is Too Wide for a True MVP

"All space types" with 15–30 suppliers and three budget tiers is not an MVP — it is a v1.0. A real MVP should prove one thing: will users who see an AI-styled room click through to purchase? Start with living rooms, two styles, one budget tier, and five to eight supplier partners.

### The AI Pipeline Is Underspecified

The document assumes photorealistic, buyable room renders but does not address how the AI maps generated furniture to real supplier SKUs. This is the hardest technical problem. Current AI generators produce beautiful rooms, but the furniture does not correspond to purchasable products. You need a product-matching layer.

### The B2B Persona Is Premature

Design offices have different onboarding, pricing, and sales cycles. Prove B2C first. B2B becomes a natural expansion once you have traction.

### No Metrics or Validation Criteria

"Validate styling-to-purchase behavior" needs concrete numbers: target conversion rate, number of beta users, time-to-first-purchase, and go/no-go signals.

# 3. Partnership Structure & Roles

Before writing a single line of code, formalize the partnership. This protects both parties and is non-negotiable for future fundraising.

## 3.1 Immediate Actions

| Action | Owner | Timeline |
| --- | --- | --- |
| Draft and sign a Co-Founder Agreement covering equity split, vesting, roles, IP ownership, and exit provisions | Both (use a lawyer) | Week 1–2 |
| Register legal entity — Saudi LLC via MISA (Ministry of Investment) or a Simplified LLC through business.sa | Both | Week 2–4 |
| Register on Maroof (online store verification platform) | Both | Week 3–4 |
| Open a joint business bank account (SAB, Al Rajhi, or SNB recommended) | Both | Week 3–4 |
| Define decision-making authority: Danah owns product/design/suppliers; Yousef owns technology and engineering | Both | Week 1 |
| Agree on initial funding: who covers pre-revenue costs (hosting, API fees, legal)? | Both | Week 1–2 |

## 3.2 Responsibility Matrix

| Domain | Danah (KASA Design) | Yousef (GulfBoost) |
| --- | --- | --- |
| Product Vision | Define user experience, styling logic, brand positioning | Technical feasibility review, effort estimation |
| Supplier Partnerships | Recruit and manage KSA supplier relationships, negotiate commissions | Build supplier onboarding portal and product feed integrations |
| AI & Engineering | Provide design expertise for training data and quality review | Select AI models, build the pipeline, develop the platform |
| Go-to-Market | Brand, social media, influencer outreach, KSA PR | Landing page, analytics, growth tooling |
| Fundraising | Pitch narrative, market storytelling, KSA/GCC investor introductions | Technical due diligence, metrics dashboards, demo builds |

# 4. Technical Architecture (KSA-Optimized)

The guiding principle is to minimize custom infrastructure and rely on managed services. Build only the parts that are your competitive advantage. All infrastructure should comply with PDPL data localization requirements.

## 4.1 Recommended Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | Next.js (React) + Tailwind CSS | Fast development, SEO-friendly, supports Arabic RTL |
| Backend API | Python (FastAPI) or Node.js (Fastify) | Python preferred for ML pipeline integration |
| Database | PostgreSQL (via Supabase or Neon) | Relational data for users, orders, products; choose ME region |
| Image Storage | AWS S3 (me-south-1 Bahrain) or Cloudflare R2 | Bahrain region for PDPL compliance and low latency |
| AI Image Generation | Stable Diffusion 3.5 via Replicate or fal.ai, or Flux | API-based, no GPU management; pay-per-render economics |
| Product Matching | CLIP embeddings + vector DB (Pinecone or Qdrant) | Match AI-rendered furniture to real supplier SKUs via visual similarity |
| Payments | Moyasar (primary) + HyperPay (fallback) | SAMA-licensed, Mada debit support, marketplace split payments, Apple Pay, STC Pay. SAR settlements. |
| BNPL | Tamara + Tabby | Both dominant in KSA. Sharia-compliant installments (2–4 payments). Merchants paid upfront regardless of customer default. |
| Auth | Phone OTP (primary) + Nafath (optional for KYC) | 75% of Saudi adults use Nafath; phone OTP standard for e-commerce |
| Hosting | Vercel (frontend) + Railway or AWS ME (backend) | Bahrain region for data residency compliance |
| Analytics | PostHog or Mixpanel | Event tracking, funnel analysis, user behavior |
| Localization | next-intl or next-i18n | Arabic (primary) + English; full RTL support required |

## 4.2 KSA Payment Architecture

Stripe does not operate in Saudi Arabia. The payment stack must be built on SAMA-licensed local gateways:

| Provider | Role | Key Features | Fees |
| --- | --- | --- | --- |
| Moyasar | Primary payment gateway | Mada, Visa/MC, Apple Pay, STC Pay, marketplace splits, SAR settlement | ~2.8–3.5% + 1 SAR/txn |
| HyperPay | Backup gateway | Mada, cards, e-wallets, T+1 settlement, AI fraud detection | ~2.8–4% per txn |
| Tamara | BNPL option 1 | Split in 2–4 payments, Sharia-compliant, merchant paid upfront | Merchant acquisition model |
| Tabby | BNPL option 2 | 4 interest-free installments, PCI DSS certified | Merchant acquisition model |

Critical: Moyasar’s marketplace feature enables split payments — when a user buys a room of furniture from multiple suppliers, Moyasar can automatically split the payment and settle each supplier’s share. This is essential for the multi-vendor model.

## 4.3 The Critical Technical Challenge: Product Matching

This is the make-or-break problem. The realistic pipeline:

- User uploads a room photo. The system analyzes the room’s dimensions, lighting, and existing elements using a vision model (e.g., GPT-4V or a fine-tuned segmentation model).

- Based on preferences (style, budget in SAR), the system selects real products from the supplier catalog that fit the room and budget.

- A prompt is constructed describing the room with those specific products. The AI image generator renders the styled room.

- The rendered furniture will never be pixel-perfect matches. Each item is paired with the closest real product using CLIP-based visual similarity search.

- The user sees the styled room with product cards overlaid (prices in SAR), each linking to the real purchasable item.

MVP Shortcut: Pre-curate product bundles (e.g., “Modern Living Room — Mid Budget SAR 8,000–12,000” = specific sofa + coffee table + rug + lamp from KSA partners). The AI renders using those products as the style guide, and the shopping list is already known. This avoids the hardest matching problem and lets you validate purchase behavior first.

# 5. Phased Development Roadmap

## Phase 0: Foundation (Weeks 1–4)

Goal: Legal setup, technical spike, and supplier outreach in parallel.

| Track | Tasks | Deliverable |
| --- | --- | --- |
| Legal & Business | Sign co-founder agreement, register Saudi LLC via business.sa, register on Maroof, open business bank account, file ZATCA VAT registration if applicable | Registered entity with signed agreements |
| Technical Spike | Prototype AI pipeline: test Stable Diffusion 3.5 / Flux via Replicate with 5 sample KSA rooms; evaluate quality and cost per render | Working prototype: room photo in, styled version out |
| Supplier Outreach | Danah identifies 8–10 KSA furniture suppliers (IKEA Saudi, Home Centre, Al-Rugaib, Almutlaq, etc.); negotiate pilot commission terms (aim for 12–15%) | Signed LOIs or pilot agreements with 3–5 suppliers |
| Product Catalog | Collect product images, SAR prices, dimensions, descriptions from suppliers; build standardized product DB | Structured database with 50–100 SKUs, all priced in SAR |
| Brand & Domain | Secure .sa or .com domain, create bilingual brand identity (Arabic + English), set up social accounts (Instagram, X, TikTok, Snapchat) | Brand kit and live social accounts |

## Phase 1: Build the MVP (Weeks 5–12)

Goal: A working product that one real user can go through end-to-end.

| Week | Focus | Details |
| --- | --- | --- |
| 5–6 | Core Frontend | Bilingual landing page (AR/EN), room upload flow, preference selection (2 styles, 1 budget tier), phone OTP auth |
| 5–6 | AI Pipeline v1 | Room analysis + styled render generation using pre-curated product bundles; target <60 second render time |
| 7–8 | Product Display | Render results page showing 2–3 styled concepts, product cards with SAR prices overlaid, “view product” links |
| 7–8 | Supplier Integration | Product feed ingestion, inventory sync (manual CSV for MVP), affiliate link or direct cart integration with KSA suppliers |
| 9–10 | Checkout Flow | Unified cart, Moyasar checkout (Mada + Visa/MC + Apple Pay + STC Pay), Tamara/Tabby BNPL integration, commission tracking |
| 11–12 | Polish & QA | RTL layout polish, mobile responsiveness, loading states, error handling, Arabic copy review, 10-person closed alpha |

## Phase 2: Closed Beta (Weeks 13–18)

Goal: Validate the core hypothesis with real users spending real SAR.

| Activity | Target | Success Metric |
| --- | --- | --- |
| Recruit 50–100 beta users via Instagram, Snapchat, Danah’s design network, and targeted KSA ads | 100 beta signups | At least 50 active users completing the full flow |
| Track full funnel: upload → styled → product click → add to cart → purchase | Full funnel data | Upload-to-purchase conversion > 3% |
| Collect qualitative feedback via short surveys and 10 user interviews (Arabic) | Actionable insights | Clear signal on what users love, tolerate, and hate |
| A/B test 2 style options and measure preference + purchase behavior | Statistical significance | One style outperforms by >20% in engagement |
| Monitor AI render quality: acceptance rate of first renders | Quality baseline | First-render acceptance rate > 40% |
| Track which KSA suppliers’ products get clicked and bought most | Supplier data | Identify top 10 performing SKUs |

## Phase 3: Iterate & Expand (Weeks 19–30)

Goal: Based on beta data, expand scope and prepare for fundraising.

- Add 2–3 more styles based on beta demand (the MVP doc suggests Japandi, Classic, Minimal, Cozy — let data decide what resonates in KSA)

- Expand KSA supplier network to 15–20 partners across budget tiers (SAR 3,000–8,000 / SAR 8,000–20,000 / SAR 20,000+)

- Build dynamic product-matching pipeline (CLIP embeddings) to replace pre-curated bundles

- Add item swap/refine functionality (replace a sofa in the render, see room update)

- Implement Lock & Buy: 24–72 hour room lock with single Moyasar checkout

- Expand BNPL: Tamara long-term installments (up to 24 months) for high-value rooms

- Launch premium tier: unlimited renders, advanced Style DNA, saved room profiles

## Phase 4: Fundraise-Ready (Weeks 28–36)

Run Phases 3 and 4 in parallel from week 28. Fundraising preparation requires a clear story and promising early data, not a complete product.

# 6. Estimated MVP Budget (SAR)

Rough estimates for Phase 0–2 (first 18 weeks). Assumes founders cover their own labor.

| Category | Estimated Cost | Notes |
| --- | --- | --- |
| Legal (LLC registration, agreements, Maroof, trademark) | SAR 8,000–20,000 | LLC registration ~SAR 2,000; lawyer fees for co-founder agreement varies |
| AI API costs (Replicate / fal.ai) | SAR 2,000–6,000/month | ~$0.05–$0.15 per render; 1,000–10,000 renders/month |
| Hosting & infrastructure | SAR 400–1,200/month | Vercel free tier + backend ~SAR 100/mo + DB ~SAR 100/mo |
| Domain, brand design, Arabic typography | SAR 1,500–5,000 | One-time; bilingual brand kit |
| Marketing (beta acquisition) | SAR 2,000–8,000 | Instagram/Snapchat/TikTok ads targeting KSA |
| Moyasar + payment processing | ~2.8–3.5% + SAR 1 per transaction | No upfront cost; transaction-based |
| ZATCA VAT compliance setup | SAR 1,000–3,000 | Accounting software + initial ZATCA registration |
| Total Phase 0–2 estimate | SAR 20,000–60,000 | ~$5,300–$16,000 USD; excludes founder salaries |

Key assumption: Both founders contribute their labor without salary during the MVP phase. If either party needs compensation, budget accordingly and document it in the co-founder agreement.

# 7. Fundraising Strategy

## 7.1 What Investors Will Ask

| Question | What They Want to See |
| --- | --- |
| Is there real demand in KSA? | Beta conversion data: X% of users who saw a styled room clicked through to buy. Testimonials from Saudi users. Waitlist numbers. |
| Can the AI produce buyable rooms? | Live demo. Room upload → styled render with real purchasable products from KSA suppliers in under 60 seconds. |
| What are the unit economics? | Cost per render vs. average commission per purchase in SAR. Path to positive unit economics at KSA price points. |
| Why this team? | Danah: design authority, KSA supplier relationships (KASA Design). Yousef: technical execution (GulfBoost). Both sides of the marketplace covered. |
| How big is the KSA market? | KSA online furniture: SAR 10B+ (2025), growing 19% CAGR to SAR 49B by 2034. KSA e-commerce overall: SAR 117B (2026). Vision 2030 housing boom. |

## 7.2 Fundraising Timeline & Target

| When | Milestone | Fundraising Action |
| --- | --- | --- |
| Weeks 1–12 | MVP built | Do not fundraise. Build. |
| Weeks 13–18 | Beta with 50–100 KSA users | Begin warm introductions to KSA/GCC angels and early-stage VCs (STV, Raed Ventures, Shorooq, Hala Ventures) |
| Weeks 19–24 | Traction data | Formal fundraise. Target: SAR 1M–3M pre-seed / seed round. |
| Weeks 25–36 | Growing user base | Close the round. Use funds for: engineering hire, marketing, supplier expansion, AI infra. |

Target raise: SAR 1M–3M (~$250K–$750K) at a SAR 8M–20M valuation. This funds 12–18 months of runway covering engineering hires, scaled AI infrastructure, marketing, and supplier expansion across KSA.

# 8. KSA Legal & Compliance Checklist

| Requirement | Details | Timeline |
| --- | --- | --- |
| Business registration | Register via business.sa (Saudi Business Center); obtain e-commerce license from Ministry of Commerce | Week 2–4 |
| Maroof registration | Register on Maroof platform for online store verification — builds consumer trust | Week 3–4 |
| VAT (ZATCA) | Register if annual turnover > SAR 375,000; mandatory e-invoicing for all B2C transactions | Before first sale |
| PDPL compliance | Personal Data Protection Law: data localization required; customer data must be stored in KSA/ME region (AWS Bahrain) | By launch |
| Arabic content | All product info, terms, return policies must be available in Arabic; commercial registration number displayed on site | By launch |
| SAMA payment compliance | Only use SAMA-licensed gateways (Moyasar, HyperPay); mandatory Mada support | By checkout implementation |
| Consumer protection | Clear return/refund policies, delivery terms, and complaint mechanism required by law | By launch |

# 9. Key Risks & Mitigations

| Risk | Severity | Mitigation |
| --- | --- | --- |
| AI renders don’t look good enough for KSA aesthetics | High | Invest in prompt engineering with KSA-style interiors during Phase 0. Use ControlNet for structural accuracy. Set quality bar before launch. |
| Product matching inaccuracy | High | MVP: pre-curated bundles. Phase 3: CLIP-based matching with human review. |
| KSA suppliers refuse or offer low commissions | Medium | Start with partners who already sell online. Offer exclusivity as incentive. Danah’s industry relationships are key. |
| Users generate renders but don’t buy | Medium | Core hypothesis being tested. If conversion <1% after beta, pivot before scaling. |
| PDPL compliance complexity | Medium | Use AWS Bahrain region from day one. Engage a KSA data privacy consultant early. |
| Competitors add commerce features | Medium | Speed to market. Your advantage is the commerce integration, not AI generation. |
| Co-founder disagreement | Medium | Thorough co-founder agreement with vesting, decision rights, IP, and exit scenarios. |

# 10. Your Immediate Next Steps

Here is exactly what you and Danah should do in the next two weeks:

### This Week (Week 1)

- 90-minute alignment meeting. Walk through this roadmap. Agree on Phase 0 scope and who does what.

- Agree on equity split, vesting, and roles in writing (even informally before the lawyer drafts it).

- Yousef: Sign up for Replicate or fal.ai. Upload 3 KSA-style room photos, generate styled outputs, evaluate quality and cost.

- Danah: Draft a list of 10 target KSA suppliers. Prioritize those with online stores and product feeds (IKEA Saudi, Home Centre, Al-Rugaib, etc.).

- Both: Agree on a working name and secure the .com and/or .sa domain.

### Next Week (Week 2)

- Engage a Saudi startup lawyer: co-founder agreement, LLC registration via business.sa.

- Yousef: Set up dev environment — GitHub repo, Next.js scaffold with Arabic RTL support, CI/CD, staging.

- Danah: Begin supplier conversations. Frame as: zero cost pilot, commission-only, new AI-driven sales channel.

- Both: Define MVP success criteria. Example: “Validated if 5 of 50 beta users complete a purchase within 30 days of first use.”

The KSA market is ready. Build the confidence engine.

Online furniture in Saudi Arabia is growing at 19% annually. Vision 2030 is driving a housing boom. No one has nailed the gap between inspiration and checkout. You have the design authority and the technical capability to fill it.

ابنِ المستقبل. Build the future.